## Screens
Module | Group | Screen | Sx | HTML Dev | HTML Status | Code Dev | Code Status
Common | User | Login | S2 | Thu | Done | Tài, Chí | Done
Common | User | ResetPass | S2 | Thu | Done | Tài, Chí | Done
Common | User | NewPass | S2 | Thu | Done | Tài, Chí | Done
Common | User | Register | S2 | Thu | Done | Hiếu | Done
Common | User | UserProfile | S2 | Hiếu | Done | Hiếu | Done
Public | Common | Home | S2 | Tú | Done | Tú, Quyết | Done
Public | Common | Search | S2 | Quyết | Done | Quyết, Tú | Done
Public | Common | Contact | S1 | Hiếu | Done | Hiếu | Done
Public | Blog | Blogs List | S3 | Tú | Done | Luân, Quyết | Done
Public | Blog | Blog Details | S3 | Tú | Done | Quyết | Done
Course Order | Cart | Course Register | S3 | Tú | Done |  | Pending
Course Order | Cart | Cart Details | S3 | Tú | Done | Luân, Tú | Done
Course Order | Cart | Order Details | S2 | Tú | Done | Luân, Tú | Done
Course Order | Cart | Order Details | S2 | Tú | Done | Luân, Tú | Done
Course Order | Cart | Order History | S2 | Tú | Done | Luân, Tú | Done
Learning | Course | Courses List | S2 | Tú | Done | Quyết | Done
Learning | Course | Course Details | S2 | Hiếu | Done | Tài, Hiếu | Done
Learning | Course | My Courses |  | Tú | Done | Luân | Done
Learning | Course | Course Study |  | Chí | Done | Chính | Done
Admin | Public Info | Sliders Mgnt |  | Thu | Done | Thu | Done
Admin | Public Info | Post Mgnt |  | Thu | Done | Thu | Done
Admin | Public Info | Contact Info | S1 | Thu | Done | Tài | Done
Admin | Learning Info | Course Mgnt |  | Chí | Done | Chính | Done
Admin | Learning Info | Course Orders |  | Thu | Done | Tài | Done
Admin | System Config | System Setting | S1 | Chính | Done | Chính | Doing
Admin | System Config | User Mgnt | S2 | Thu | Done | Tài, Thu | Done
Admin | System Config | Menu Mgnt |  | Thu | Done | Chí | Doing
Admin | System Config | Permission Mgnt |  | Thu | Done | Tài, Thu | Doing
Admin | System Config | Lesson/Document Mgnt |  |  |  |  | Pending
Admin | System Config | Role Mgnt |  | Thu | Done | Tài, Thu | Done
Public | Course | Favorite |  | Hiếu | Done | Hiếu | Done

## Team
Task Grouip | Task Details | Incharge | Status
HTML | Xem Screens
FE | Xem Screens
BE | User | Luân | Done
BE | Course | Tài | Done
BE | UserCourse | Tài | Done
BE | Slider | Tài | Done
BE | Role | Tài | Done
BE | Setting | Tài | Done
BE | Document | Luân | Done
BE | Favorite | Luân | Done
BE | Progress | Luân | Done
BE | Category | Quyết | Done
BE | Group | Quyết | Done
BE | Order | Quyết | Done
BE | Permission | Quyết | Done
BE | Post | Chính | Done
BE | Contact | Chính | Done
BE | Lesson | Chính | Done
BE | Registration | Chính | Done